## Summary
CareNest — Final Wrap-Up Checklist
Generated 19 Aug 2026 — audited against live code, not the stale task-plan xlsx
Tasks by owner
Person A (Backend / Data) | 35
Person B (Frontend / UX / Docs) | 33
Shared / Together | 7
Total tasks | 69
Progress by status
Not started | 66
In progress | 0
Done | 3
Blocked | 0
% Complete | 4.348%
Tool key
Claude Design | Build the CareNest component kit (fields, buttons, consent modal, badges) as one reviewable source of truth.
Cowork | Code edits, forms, migrations, tests, docs, the final report — this session.
Manual | manage.py commands, clicking through roles, screenshots, recordings, author judgment calls.
Parallel-work rules
- Only Person A creates migrations. If B needs a model field, B asks A.
- Only Person A touches config/settings.py.
- Only Person B touches CSS and templates/. A touches .py files.
- accounts/forms.py + views.py are A's; accounts/templates/ is B's — same feature, no conflict.
- Pull before you push, every time — two active branches.
- Nobody edits reports/ at the same time — agree an owner for the diary and report file.
Three handoff points (B waits on A)
1. A ships password-reset URLs -> B builds the 4 templates
2. A adds the terms checkbox field -> B writes the markup and wording
3. A's temperature/SpO2 migration lands -> B adds the vitals inputs

## Checklist
| ID | Task | Owner | Tool to use | Priority | Depends on / Handoff | Notes | Status
PHASE 0 — Together first | 0.1 | Run manage.py migrate | Both | Manual | Blocking |  | DB was missing ~15 tables incl. DoseTime, CarePlan, LabReport. DONE 2026-08-19. | Done
PHASE 0 — Together first | 0.2 | Run full test suite, record pass/fail count | Person A | Manual | High |  | Number goes in the report's testing chapter | Not started
PHASE 0 — Together first | 0.3 | Run generate_cohort then train_models | Person A | Manual | High |  | Current metrics.json trained on 6 patients only - not usable | Not started
PHASE 0 — Together first | 0.4 | Agree final project name: CareNest vs Smart Health Companion | Both | Manual | High |  | Code says CareNest; decks/task plan say the other | Not started
PHASE 0 — Together first | 0.5 | Agree who owns the diary and final report file | Both | Manual | Medium |  |  | Not started
A1. Auth fixes | A1.1 | Make email unique on User model + migration | Person A | Cowork | High |  | DONE 2026-08-19 - migration 0009 applied | Done
A1. Auth fixes | A1.2 | Simplify _username_for_login now that email is unique | Person A | Cowork | Medium | Depends on A1.1 | DONE 2026-08-19 | Done
A1. Auth fixes | A1.3 | Add password reset (views/urls/templates) | Person A + Person B | Cowork | High | A ships URLs, then hands off to B for templates | Biggest functional gap - no reset exists at all | Not started
A1. Auth fixes | A1.4 | Add rate limiting / lockout on failed logins | Person A | Cowork | High |  | django-axes or cache-backed counter | Not started
A1. Auth fixes | A1.5 | Add session security settings in settings.py | Person A | Cowork | Medium |  | SESSION_COOKIE_SECURE, CSRF_COOKIE_SECURE, expiry etc. | Not started
A1. Auth fixes | A1.6 | Flip DEBUG default to False | Person A | Cowork | Medium |  |  | Not started
A1. Auth fixes | A1.7 | Move password rules into RegisterForm.clean() | Person A | Cowork | Low |  |  | Not started
A1. Auth fixes | A1.8 | Move __init__ below field declarations in RegisterForm | Person A | Cowork | Low |  |  | Not started
A1. Auth fixes | A1.9 | Add phone number RegexValidator | Person A | Cowork | Medium |  |  | Not started
A1. Auth fixes | A1.10 | Build a real ProviderOnboardingForm (validate 5 credential fields) | Person A | Cowork | Medium |  |  | Not started
A1. Auth fixes | A1.11 | Add terms/privacy consent checkbox at registration | Person A + Person B | Cowork | High | A adds field, hands off to B for markup/wording | Log acceptance to AuditLog | Not started
A1. Auth fixes | A1.12 | Note deliberate generic login error message in report | Person A | Cowork | Low |  |  | Not started
A2. Schema fixes | A2.1 | Add temperature and spo2 to VitalRecord | Person A | Cowork | High | Hands off to B for vitals form fields | Docs claim BP/HR/temp/SpO2 but columns don't exist | Not started
A2. Schema fixes | A2.2 | Make bp_systolic / bp_diastolic nullable | Person A | Cowork | Medium |  |  | Not started
A2. Schema fixes | A2.3 | Bound numeric vitals fields (min/max validators) | Person A | Cowork | Medium |  |  | Not started
A2. Schema fixes | A2.4 | Decide fate of Medication.schedule free-text field | Person A | Cowork | Low |  |  | Not started
A2. Schema fixes | A2.5 | Check what HealthDocument actually stores; document it | Person A | Cowork | Medium |  |  | Not started
A2. Schema fixes | A2.6 | Add DB indexes (VitalRecord, MedicationDose, ConsentGrant, AuditLog) | Person A | Cowork | Medium |  |  | Not started
A2. Schema fixes | A2.7 | Squash or document the merged migration tree | Person A | Cowork | Low |  |  | Not started
A2. Schema fixes | A2.8 | Decide MySQL vs SQLite for submission and state why | Person A | Cowork | Low |  |  | Not started
A2. Schema fixes | A2.9 | Defend 10-boolean ConsentGrant design in report (no refactor) | Person A | Cowork | Low |  |  | Not started
A3. Data science | A3.1 | Build medication non-adherence model (4.2) | Person A | Cowork | High | Start after 0.3 finishes |  | Not started
A3. Data science | A3.2 | Build health-risk prediction model (4.3) | Person A | Cowork | High | Start after 0.3 finishes |  | Not started
A3. Data science | A3.3 | Build vitals anomaly detection model (4.4) | Person A | Cowork | High | Start after 0.3 finishes |  | Not started
A3. Data science | A3.4 | Decide on mood/sentiment model (4.6): build or document exclusion | Person A | Cowork | Medium |  |  | Not started
A3. Data science | A3.5 | Write CRISP-DM documentation per model (4.8) | Person A | Cowork | High |  | Explicitly required for MDS grading | Not started
A3. Data science | A3.6 | Build monitoring engine - vitals-anomaly alerts (3.14) | Person A | Cowork | Medium | Hands off to B for dashboard 3.30 | Medication alerts already done | Not started
A4. Tests | A4.1 | Deletion-verification test (5.3) | Person A | Cowork | High |  | Proves the process-and-discard privacy claim | Not started
A4. Tests | A4.2 | End-to-end 5-role journey tests (5.6) | Person A | Cowork | Medium |  |  | Not started
A4. Tests | A4.3 | Consent audit-trail assertions (5.7) | Person A | Cowork | Medium |  |  | Not started
A4. Tests | A4.4 | Extend EveryPageRendersTests to new pages | Person A | Cowork | Low |  |  | Not started
B1. Cleanup | B1.1 | Delete ~24 stray root-level HTML mockups | Person B | Cowork | Medium |  |  | Not started
B1. Cleanup | B1.2 | Clear out venv.zip, backup tar.gz, db backup files | Person B | Cowork | Low |  |  | Not started
B1. Cleanup | B1.3 | Consolidate shc.css and dashboard CSS into one file | Person B | Cowork | Medium |  |  | Not started
B1. Cleanup | B1.4 | Rename anything still called shc to CareNest | Person B | Cowork | Low |  |  | Not started
B2. Component library | B2.1 | Build CareNest component kit (fields, buttons, cards, modal, badges) | Person B | Claude Design | High |  |  | Not started
B2. Component library | B2.2 | Extract shared _consent_modal.html partial | Person B | Cowork | Medium |  |  | Not started
B2. Component library | B2.3 | Apply kit classes across templates | Person B | Cowork | Medium |  |  | Not started
B2. Component library | B2.4 | Diff the six provider dashboards for inconsistency | Person B | Cowork | Low |  |  | Not started
B2. Component library | B2.5 | Chart consistency pass (vitals + DS analytics) | Person B | Claude Design / Cowork | Low |  |  | Not started
B3. Registration & login UX | B3.1 | Verify conditional field reveal works (role radio -> fields) | Person B | Manual | Medium |  |  | Not started
B3. Registration & login UX | B3.2 | Add password strength meter | Person B | Claude Design | Low |  |  | Not started
B3. Registration & login UX | B3.3 | Add show-password toggle | Person B | Claude Design | Low |  |  | Not started
B3. Registration & login UX | B3.4 | Build the 4 password-reset templates | Person B | Cowork | High | Blocked until A ships reset URLs (A1.3) |  | Not started
B3. Registration & login UX | B3.5 | Build terms checkbox markup and wording | Person B | Cowork | Medium | Blocked until A adds form field (A1.11) |  | Not started
B3. Registration & login UX | B3.6 | Add temperature/SpO2 inputs to vitals form | Person B | Cowork | Medium | Blocked until A's migration lands (A2.1) |  | Not started
B4. Field audit | B4.1 | Build the page-by-page field audit sheet (24+ pages) | Person B | Cowork | High |  |  | Not started
B4. Field audit | B4.2 | Verify every field has a bound <label> | Person B | Manual | Medium |  |  | Not started
B4. Field audit | B4.3 | Rewrite error messages in plain language | Person B | Cowork | Medium |  |  | Not started
B4. Field audit | B4.4 | Verify every page renders/403s correctly per role | Person B | Manual | Medium |  |  | Not started
B4. Field audit | B4.5 | Report bare request.POST.get() views (no Form class) to A | Person B | Manual | Medium |  |  | Not started
B5. UX passes | B5.1 | Accessibility pass (font size, tap targets, contrast, focus) | Person B | Manual + Claude Design | High |  | Target users are elderly/low-tech | Not started
B5. UX passes | B5.2 | Count consent-modal fatigue across a realistic session | Person B | Manual | Medium |  |  | Not started
B5. UX passes | B5.3 | Walk through error-recovery paths (OCR miss, rejected link, etc.) | Person B | Manual | Medium |  |  | Not started
B5. UX passes | B5.4 | Check empty states on all pages | Person B | Manual | Low |  |  | Not started
B5. UX passes | B5.5 | Test all five dashboards at 375px mobile width | Person B | Manual | Medium |  |  | Not started
B6. Documentation & assets | B6.1 | Screenshot every page for report appendix | Person B | Manual | Medium | Do after Phase 0 migrate |  | Not started
B6. Documentation & assets | B6.2 | Update task tracker xlsx to match real status | Person B | Cowork | Medium |  |  | Not started
B6. Documentation & assets | B6.3 | Add project diary entries for 17-18 August | Person B | Cowork | Medium |  |  | Not started
B6. Documentation & assets | B6.4 | Update Demo-2 deck | Person B | Cowork | Medium |  |  | Not started
B6. Documentation & assets | B6.5 | Record demo screencast | Person B | Manual | Low | Needs a working system - do late |  | Not started
CONVERGE — Together at the end | C.1 | Deployment / demo setup | Person A | Manual | Medium | Person B verifies |  | Not started
CONVERGE — Together at the end | C.2 | Write final project report | Person A + Person B | Cowork | High | A: architecture/data/DS/testing. B: UI/UX/journeys/figures. | One person owns the merge | Not started
CONVERGE — Together at the end | C.3 | Final read-through together | Both | Manual | High |  | Check name consistency, numbers match generated metrics | Not started