## Summary
Smart Health Companion — Post-Review Build Plan
Owner split (Frontend member vs Backend member); 'Both' = collaborate
Tasks by Owner | Count
Backend member
Frontend member
Both (shared)
Total tasks
Progress by Status | Count
Not started
In progress
Done
Blocked
% Complete
Note on balance
Split follows a full-stack division: Backend member owns models, business logic, the extraction/consent engines, and the
data-science models; Frontend member owns all five role dashboards, forms, charts, the consent-popup UX, diagrams, and the deck.
Backend has a few more discrete rows because the DS models sit there, but each Frontend UI task (role dashboards, responsive,
accessibility) is individually larger — so effort is balanced. Swap any row's Owner via the dropdown to rebalance.
Legend: Effort S/M/L = small/medium/large. Status dropdown drives the % Complete above.

## Task Tracker
Phase | ID | Task | Owner | Effort | Depends On | Status | Notes
1 — Lock Scope & Docs | 1.1 | Record scope redefinition in project diary (DDI dropped, process-and-discard, consent-everywhere, new users, nursing added) | Both | S | — | Done | The 'why we changed' record after review feedback
1 — Lock Scope & Docs | 1.2 | Rewrite problem statement, objectives & business problems (remove DDI BP3; add 2 provider-side BPs) | Both | M | 1.1 | Done | Blocks the redesign
1 — Lock Scope & Docs | 1.3 | Finalize value proposition & target-user definition (continuity-of-care companion; chronic/elderly + caregiver/nurse) | Both | S | 1.1 | Done | Answers the 'why the app if they have a doctor' question
1 — Lock Scope & Docs | 1.4 | Update review deck to reflect new scope | Both | M | 1.2,1.3 | Done | Reuse existing deck; strip DDI & storage slides
2 — Redesign Artifacts | 2.1 | Remove DDI from design; design medication-card replacement + 'show your doctor' prompt | Both | S | 1.2 | Done | Non-clinical alternative to interaction checker
2 — Redesign Artifacts | 2.2 | Redesign document handling as process-and-discard pipeline | Both | M | 1.2 | Done | upload > extract > verify > save structured > delete
2 — Redesign Artifacts | 2.3 | Design consent framework (events, granularity, consent log, withdrawal) | Both | M | 1.2 | Done | Fires on every extract & share
2 — Redesign Artifacts | 2.4 | Design nursing role (placement, assignment, visit, escalation) | Both | M | 1.2 | Done | Decide: own role vs provider subtype
2 — Redesign Artifacts | 2.5 | Define provider use cases (verification, snapshot, care plan, monitoring, coordination) | Both | M | 1.2 | Done | Balances the patient-heavy use-case set — 28 implemented use cases + 8 planned, each mapped to a real URL — docs/use_cases.md. [verified against code 2026-08-03]
2 — Redesign Artifacts | 2.6 | Update ERD / data model (drop DrugInteraction & media entities; add Consent, NursingVisit, CarePlan, ProviderService) | Both | M | 2.1,2.2,2.3,2.4 | Done | Foundation for all models — ERD generated from Django model introspection — docs/erd.md + reports/figures/erd.png¦svg. [verified against code 2026-08-03]
2 — Redesign Artifacts | 2.7 | Update architecture diagram (intelligence layer loses DDI; data layer loses media store; add consent service) | Both | S | 2.6 | Done | Visual/diagram work — Layered architecture + consent-gated-read sequence diagram — docs/architecture.md. [verified against code 2026-08-03]
2 — Redesign Artifacts | 2.8 | Update use-case diagram (add provider + nurse actors/cases) | Both | S | 2.5 | Done | Visual/diagram work — Actor/use-case diagram rendered — reports/figures/use_cases.png¦svg. [verified against code 2026-08-03]
2 — Redesign Artifacts | 2.9 | Revise module list (13 modules -> new set) | Both | S | 2.5,2.6 | Done | Keep numbering consistent across docs — 22 modules with implemented/planned status; records the 2 removed modules — docs/modules.md. [verified against code 2026-08-03]
2 — Redesign Artifacts | 2.10 | Wireframe all five role dashboards | Both | L | 2.9 | Done | Patient/caregiver/nurse/provider/admin — As-built layouts for all 5 role dashboards + 12 full-page screenshots — docs/wireframes.md. [verified against code 2026-08-03]
2 — Redesign Artifacts | 2.11 | Design consent pop-up UX & flows (plain-language, large-text, accessible) | Both | M | 2.3 | Done | Must not cause consent fatigue for elderly — Consent pop-up UX for elderly/low-tech users incl. accessibility — docs/consent_ux.md. [verified against code 2026-08-03]
2 — Redesign Artifacts | 2.12 | Design navigation / information architecture for 5 roles | Both | M | 2.10 | Done | Role-based routing map — Per-role navigation map derived from sidebar partials and URLs — docs/information_architecture.md. [verified against code 2026-08-03]
3 — Build (Backend) | 3.1 | Django project config, settings, env, MySQL setup | Both | S | 2.6 | Done | Scaffold already exists (venv/Django 6) — Django config, settings, .env. Running on SQLite (USE_SQLITE=1); MySQL path kept. [verified against code 2026-08-03]
3 — Build (Backend) | 3.2 | Custom User model + RBAC + roles (incl. nurse) | Both | M | 3.1 | Done | Role discriminator on single User entity — Custom User, 5 roles incl. Nurse, role_required decorator, tested. [verified against code 2026-08-03]
3 — Build (Backend) | 3.3 | Patient profile & onboarding (models + logic) | Both | M | 3.2 | Done | Profile fields + progressive completion indicator; patients skip the wizard. [verified against code 2026-08-03]
3 — Build (Backend) | 3.4 | Vitals models + anomaly-detection logic | Both | M | 3.3 | Done | Threshold rules for BP/HR/temp/SpO2 — VitalRecord.compute_status() threshold rules + health/analytics.py insight rules. [verified against code 2026-08-03]
3 — Build (Backend) | 3.5 | Medication & inventory models + medication-card logic | Both | M | 3.3 | Done | Card replaces the DDI checker — Medication + MedicationDose per-day tracking, adherence %, medication card UI. [verified against code 2026-08-03]
3 — Build (Backend) | 3.6 | Prescription/lab extraction pipeline (OCR+LLM) with process-and-discard + verify | Both | L | 2.2,3.5 | Not started | Ensure no residual files / no LLM retention
3 — Build (Backend) | 3.7 | Consent engine: gating decorators/middleware, consent log, withdrawal | Both | L | 2.3,3.2 | Done | Gate every extract & share action — ConsentGrant model, has_consent() gate, revoke/expiry, audit-logged. [verified against code 2026-08-03]
3 — Build (Backend) | 3.8 | Appointments & reminders logic | Both | M | 3.2 | Done | Appointment request/accept/decline/complete loop. [verified against code 2026-08-03]
3 — Build (Backend) | 3.9 | Caregiver module logic | Both | M | 3.2 | Done | CaregiverLink + patient-side approval gating all caregiver access. [verified against code 2026-08-03]
3 — Build (Backend) | 3.10 | Nurse module: assignment, visit logging, escalation, data-entry-on-behalf | Both | L | 2.4,3.2 | Done | Logging/coordination only, not clinical orders — nursing app: NurseAssignment, NursingVisit, escalation, nurse-tagged vitals. [verified against code 2026-08-03]
3 — Build (Backend) | 3.11 | Provider marketplace: verification, listings, availability | Both | L | 3.2 | In progress | Verification + listings done; availability calendar outstanding (Phase 3). [verified against code 2026-08-03]
3 — Build (Backend) | 3.12 | Pre-visit snapshot API (consented, read-only) | Both | M | 3.7,3.11 | Not started | Highest-value provider feature
3 — Build (Backend) | 3.13 | Care plan / targets logic | Both | M | 3.11 | Not started | Provider sets targets -> patient dashboard
3 — Build (Backend) | 3.14 | Remote monitoring + alerts engine | Both | L | 3.4,3.11 | Not started | Anomaly & missed-dose alerts to provider/nurse
3 — Build (Backend) | 3.15 | Secure sharing as ephemeral pass-through (no persistence) | Both | M | 3.7 | In progress | App is a pipe, not a vault — ConsentGrant revoke/expiry works; purge command + pass-through hardening outstanding. [verified against code 2026-08-03]
3 — Build (Backend) | 3.16 | Admin & provider-verification logic | Both | M | 3.11 | Done | Admin verification queue with approve / request-info, suspend/reinstate, AuditLog. [verified against code 2026-08-03]
3 — Build (Frontend) | 3.17 | Base templates, layout, Bootstrap theme, responsive shell | Both | M | 2.12 | Done | base_dashboard.html + 5 role sidebars + dashboard.css design system. [verified against code 2026-08-03]
3 — Build (Frontend) | 3.18 | Auth / login / register UI (all roles) | Both | M | 3.17,3.2 | Done | Real register/login/logout for all roles; Nurse & Admin not self-registerable. [verified against code 2026-08-03]
3 — Build (Frontend) | 3.19 | Patient dashboard + onboarding forms | Both | M | 3.17,3.3 | Done | Patient dashboard driven by real data + profile completion prompt. [verified against code 2026-08-03]
3 — Build (Frontend) | 3.20 | Vitals entry forms + trend charts | Both | M | 3.19,3.4 | Done | Follow dataviz guidance for charts — Vitals form saving to DB; trend sparklines computed server-side from real readings. [verified against code 2026-08-03]
3 — Build (Frontend) | 3.21 | Medication management UI + medication-card view | Both | M | 3.19,3.5 | Done | Medication UI with dose ticking and adherence display. [verified against code 2026-08-03]
3 — Build (Frontend) | 3.22 | Prescription upload UI + extraction-verify screen | Both | M | 3.21,3.6 | Not started | Show image only until confirm, then discard
3 — Build (Frontend) | 3.23 | Consent pop-up components wired to extract/share actions | Both | M | 2.11,3.7 | Not started | Reusable modal component
3 — Build (Frontend) | 3.24 | Appointments booking UI + reminders display | Both | M | 3.19,3.8 | Done | Booking UI wired to Appointment; upcoming/past lists. [verified against code 2026-08-03]
3 — Build (Frontend) | 3.25 | Caregiver dashboard | Both | M | 3.17,3.9 | Done | Caregiver dashboard, consent-gated, with waiting state before approval. [verified against code 2026-08-03]
3 — Build (Frontend) | 3.26 | Nurse dashboard: assignments, visit-logging forms, escalation UI | Both | L | 3.17,3.10 | Done | Nurse dashboard: assignments, visit logging form, escalation UI. [verified against code 2026-08-03]
3 — Build (Frontend) | 3.27 | Provider dashboard: marketplace listing, availability calendar | Both | L | 3.17,3.11 | In progress | Provider dashboard done; marketplace availability calendar outstanding (Phase 3). [verified against code 2026-08-03]
3 — Build (Frontend) | 3.28 | Pre-visit snapshot view (provider) | Both | M | 3.27,3.12 | Not started
3 — Build (Frontend) | 3.29 | Care plan / targets UI | Both | M | 3.27,3.13 | Not started
3 — Build (Frontend) | 3.30 | Remote monitoring dashboard + alert display | Both | L | 3.27,3.14 | Not started
3 — Build (Frontend) | 3.31 | Admin dashboard + verification UI | Both | M | 3.17,3.16 | Done | Admin dashboard with live KPIs, users, providers, audit log, nursing. [verified against code 2026-08-03]
4 — Data Science | 4.1 | Generate/expand synthetic dataset covering new flows (nursing visits, provider interactions, consent events) | Both | M | 2.6 | Not started | Keep <=100 records, no real patient data
4 — Data Science | 4.2 | Medication non-adherence detection/monitoring model | Both | M | 4.1 | Not started | BP1
4 — Data Science | 4.3 | Health-risk prediction model | Both | M | 4.1 | Not started | BP2
4 — Data Science | 4.4 | Vital-sign anomaly detection (rules/model) | Both | M | 4.1 | Not started | Ties to 3.4
4 — Data Science | 4.5 | Personalized recommendation engine | Both | M | 4.1 | Not started | BP4
4 — Data Science | 4.6 | Private mood / sentiment check-in | Both | S | 4.1 | Not started
4 — Data Science | 4.7 | Model evaluation & validation metrics | Both | M | 4.2,4.3,4.4,4.5 | Not started
4 — Data Science | 4.8 | CRISP-DM documentation per model | Both | M | 4.7 | Not started | Required for MDS grading
4 — Data Science | 4.9 | Analytics / DS-output visualizations & dashboards | Both | M | 4.7 | Not started | Present model outputs in-app
4 — Data Science | 4.10 | Retire the 22 MB drug-interaction CSV dependency | Both | S | 2.1 | Done | Cleanup after DDI removal — CSV + verify script moved to _to_delete/ on 2026-08-03; data/README.md rewritten. [verified against code 2026-08-03]
5 — Testing & Verify | 5.1 | Backend unit tests per module | Both | M | Phase 3 | Done | 39 automated tests across accounts, health, providers, nursing, adminpanel. [verified against code 2026-08-03]
5 — Testing & Verify | 5.2 | RBAC / permission & consent-gating tests | Both | M | 3.7 | Done | Provider sees data only after consent — RBAC + consent-gating tests incl. mental-health exclusion assertion. [verified against code 2026-08-03]
5 — Testing & Verify | 5.3 | Verify true deletion (no residual files, LLM no-retention) | Both | M | 3.6 | Not started | Proves the privacy claim
5 — Testing & Verify | 5.4 | Frontend / UI testing (all roles, responsive) | Both | M | Phase 3 | Not started
5 — Testing & Verify | 5.5 | Accessibility check (elderly-friendly: large text, simple flows) | Both | S | 5.4 | Not started | Target users are low-tech
5 — Testing & Verify | 5.6 | End-to-end journey tests (patient, caregiver, nurse, provider, admin) | Both | M | 5.1,5.4 | In progress | Per-flow tests exist; full 5-role journey tests outstanding (Phase 6). [verified against code 2026-08-03]
5 — Testing & Verify | 5.7 | Consent audit-trail verification | Both | S | 5.2 | In progress | AuditLog written on all key actions; dedicated audit assertions outstanding (Phase 6). [verified against code 2026-08-03]
6 — Deliverables | 6.1 | Final project report / thesis | Both | L | Phase 4,Phase 5 | Not started
6 — Deliverables | 6.2 | Final Demo-2 deck | Both | M | 6.1 | Not started
6 — Deliverables | 6.3 | Maintain project diary (ongoing) | Both | S | — | In progress | Update entry per work session — reports/project_diary.md maintained; add an entry per session. [verified against code 2026-08-03]
6 — Deliverables | 6.4 | Demo recording / screencast | Both | M | 5.6 | Not started
6 — Deliverables | 6.5 | Code cleanup, docstrings, README | Both | S | Phase 3 | In progress | README rewritten; docstring/cleanup pass outstanding (Phase 7). [verified against code 2026-08-03]
6 — Deliverables | 6.6 | Deployment / demo setup | Both | M | 5.6 | Not started